## Sheet1
Name | Austin Brummett
Project | Phased Array in Sound
Date | Time(hr) | Activities | Total Hours
2018-12-21 | 3 | Attempting to interface DAC with SPI | 101.3
2018-12-22 | 2 | SPI works, why won’t the dac???
2018-12-27 | 4 | Can’t test the dac w/o oscilloscope, looked into background math and theory
2019-01-14 | 0.5 | Did some research into phased arrays
2019-01-16 | 3 | Trying to get DAC to work
2019-01-19 | 0.5 | First meeting with Blandford
2019-01-21 | 2 | Working on getting hardware correct
2019-01-22 | 1.5 | Looking for new speakers per Blandford's orders
2019-01-29 | 0.5 | Blandford meeting, inline amp speakers found
2019-02-01 | 3 | Ordered speakers, found out the dac was misordered. RIP
2019-02-04 | 5 | Switched to new DAC, think I got it working and circuit is good
2019-02-05 | 2 | I was wrong something is offf
2019-02-05 | 2 | Started schematic and pcb design
2019-02-05 | 3 | PCB Desgin good, I think
2019-02-11 | 1 | Talked to Blandford
2019-02-12 | 5 | Software started and tested, got a single DAC running
2019-02-14 | 3 | Figuring out DMA
2019-02-17 | 3 | Box and lid design
2019-02-20 | 3 | Sent box & lid to Jeff & started getting DMA working with timer
2019-02-21 | 2 | Redesigned lid because it didn't fit, sent to Jeff for printing
2018-02-25 | 3 | Worked on trying to figure out why I am not getting a phase shift
2018-02-26 | 3 | Worked with Blandford fixed small issues in code and got the waves to phase shift
2019-02-28 | 1.5 | Was made aware of a too many cycles problem, in process of fixing it
2019-03-01 | 3 | Worked on poster draft and paper draft
2019-03-01 | 2 | Adjusted sine wave array to a single cycle instead of ten
2019-03-02 | 5 | Did some testing and worked on paper draft
2019-03-05 | 0.5 | Ordered PCB
2019-03-08 | 8 | Worked on arrays, can't figure out why my peaks are off
2019-03-12 | 5 | Peaks off because I screwed up my grounding
2019-03-14 | 1.5 | Poster Draft
2019-03-16 | 2.5 | worked on paper, think it is okay
2019-03-19 | 2.5 | Got PCB, started soldering and got a shelf to attach them to
2019-03-20 | 4 | Soldered pcb, it didn’t work because I missed a few connections somewhere
2019-03-23 | 3.8 | found the messed up connections after meticulously searching my monstrosity and fixed it
2019-03-24 | 1 | Fixed poster draft
2019-03-24 | 1 | fixed poster draft again
2019-04-08 | 3 | worked on final paper and made corrections
2019-04-09 | 2 | started practice presentation
2019-04-09